# Day-Of Wedding Coordinator Checklist

Forty practical checks from final handoff through the next business day. Add your own due dates, owners, and confirmed details.

Role boundary: This checklist organizes confirmed information. It does not create authority, replace vendor contracts, verify food-allergy safety, or substitute for an experienced professional when the venue, guest count, travel, cultural traditions, or production needs exceed a helper's experience.

# Four to two weeks before

| Done | When | Task + confirmation note | Owner |
| --- | --- | --- | --- |
| [ ] | 4 weeks before | Collect final contracts, arrival windows, and departure terms Confirm names, mobile numbers, load-in rules, service scope, overtime, and strike obligations. | Coordinator |
| [ ] | 4 weeks before | Build the primary and backup contact sheet Include venue escalation, every vendor lead, transportation, wedding party leads, and emergency contacts. | Coordinator |
| [ ] | 3-4 weeks before | Review the master timeline with the couple and venue Identify fixed times, flexible blocks, buffers, optional cuts, hard stops, and travel time. | Coordinator |
| [ ] | 3 weeks before | Name the day-of change authority and cue callers Record who approves timeline changes and who gives each ceremony and reception cue. | Couple / coordinator |
| [ ] | 3 weeks before | Confirm load-in, parking, storage, and accessibility routes Walk the actual entrances, elevators, restrooms, secure storage, guest route, and service route. | Coordinator / venue |
| [ ] | 2-3 weeks before | Document the weather and temperature decision plan Name the decision owner, trigger time, forecast source, alternate setup, and communication sequence. | Coordinator / venue |
| [ ] | 2-3 weeks before | Confirm guest and wedding-party transportation Verify vehicles, capacity, drivers, pickup points, buffers, parking, and missed-ride fallback. | Coordinator / transportation |
| [ ] | 2 weeks before | Review ceremony and reception layouts Check capacity, table numbers, reserved seats, vendor positions, power, exits, and step-free routes. | Coordinator / venue |
| [ ] | 2 weeks before | Confirm the family photo list and wrangler Use names and grouping order; the couple should not locate missing relatives. | Coordinator / photographer |
| [ ] | 2 weeks before | Confirm gifts, cards, personal items, rentals, and return owners Name the secure location, recipient, vehicle, inventory owner, and return deadline. | Coordinator / couple |

# Final week

| Done | When | Task + confirmation note | Owner |
| --- | --- | --- | --- |
| [ ] | 1-2 weeks before | Create role-specific schedules from the approved master Give each person only the times, locations, contacts, and cues they need; retain one source of truth. | Coordinator |
| [ ] | 5-7 days before | Confirm every vendor directly Receive an explicit yes for arrival, setup, service, departure, contact, and any change. | Coordinator |
| [ ] | 3-5 days before | Complete the final venue walkthrough Verify rooms, keys, lighting, climate, furniture, kitchen, bar, loading, cleanup, and hard stop. | Coordinator / venue |
| [ ] | 2-4 days before | Prepare the day-of document and supply kit Pack the approved timeline, contacts, layouts, cue lists, basic tools, labels, chargers, and offline copies. | Coordinator |
| [ ] | 1-2 days before | Lead or attend the ceremony rehearsal Practice lineup, pace, handoffs, seating, microphones, music, and the weather alternative. | Coordinator / officiant |
| [ ] | 1 day before | Reconfirm weather, transportation, and urgent changes Record the final decision, update the source plan, and tell only the affected people. | Coordinator |

# Wedding morning and setup

| Done | When | Task + confirmation note | Owner |
| --- | --- | --- | --- |
| [ ] | Before first vendor | Open the venue and verify life-safety and access conditions Do not improvise around blocked exits or unsafe conditions; use the venue escalation path. | Coordinator / venue |
| [ ] | At each arrival | Check in each vendor and confirm the communication path Record arrival, lead name, work area, immediate dependency, and best contact; keep the couple out of routine relays. | Coordinator |
| [ ] | During load-in | Track deliveries, inventory, and setup dependencies Photograph delivered items, note shortages or damage, and resolve guest-facing essentials first. | Coordinator / setup leads |
| [ ] | Before guest areas open | Inspect ceremony, cocktail, and reception spaces Check cleanliness, climate, lighting, sound, signage, seating, restrooms, accessibility, and weather protection. | Coordinator / venue |
| [ ] | At service start | Confirm hair and makeup order and finish target Track actual starts and alert photo before the portrait schedule is affected. | Coordinator / beauty lead |
| [ ] | Before detail photos | Gather attire, rings, stationery, flowers, and personal details Keep items together, record custody, and return valuables to the named owner. | Coordinator / designated attendant |
| [ ] | Before portraits | Confirm food, water, dressing, and travel readiness Protect health and dignity; verify people, vehicles, bouquets, accessories, and the departure cue. | Coordinator / attendants |

# Pre-ceremony

| Done | When | Task + confirmation note | Owner |
| --- | --- | --- | --- |
| [ ] | 60-90 minutes before | Complete the audio and music soundcheck Test microphones, processional and recessional tracks, power, backup audio, and pronunciations. | Coordinator / audio lead |
| [ ] | 45-60 minutes before | Confirm the ceremony is guest-ready Check reserved seats, programs, water, ushers, signage, weather plan, and accessible route. | Coordinator / ceremony lead |
| [ ] | 20-30 minutes before | Hide and line up the wedding party Verify order, bouquets, boutonnieres, rings, license, officiant, and photo/video positions. | Coordinator / wedding party lead |

# Ceremony

| Done | When | Task + confirmation note | Owner |
| --- | --- | --- | --- |
| [ ] | At processional | Cue doors, music, participants, and officiant Use one cue caller and pause when a required person or safety condition is not ready. | Ceremony cue caller |
| [ ] | During ceremony | Monitor timing and prepare the recessional transition Avoid interrupting the ceremony unless safety or the authorized recovery plan requires it. | Coordinator |

# Cocktail hour and transition

| Done | When | Task + confirmation note | Owner |
| --- | --- | --- | --- |
| [ ] | Immediately after ceremony | Direct guests and release the photo list Open the correct guest route and stage named family groups away from guest traffic. | Coordinator / ushers / family wrangler |
| [ ] | During cocktail hour | Manage room flip and reception readiness Track tables, decor, lighting, sound, catering, seating display, and completion sign-off. | Coordinator / venue / vendors |
| [ ] | 15 minutes before reception | Confirm guest seating and wedding-party lineup Resolve seating issues away from the couple and verify names and pronunciations. | Coordinator / MC |

# Reception

| Done | When | Task + confirmation note | Owner |
| --- | --- | --- | --- |
| [ ] | Before dinner | Confirm entrance, first dance, and meal-service cues Do not release a cue until the couple, camera teams, audio, room, and kitchen are ready. | Coordinator / MC / catering |
| [ ] | During dinner | Track meal service, dietary handoffs, and vendor meals Use confirmed guest and caterer information; the checklist does not verify allergy safety. | Coordinator / catering captain |
| [ ] | Before formalities | Confirm speakers, microphones, songs, cake, and camera positions Verify order and readiness before moving guests' attention or changing service flow. | Coordinator / MC |
| [ ] | During open dancing | Monitor timeline drift, breaks, bar timing, and transportation Use approved buffers and optional cuts first; only the named authority approves a timeline change. | Coordinator |
| [ ] | Before the final hour | Confirm last call, final song, send-off, and hard venue stop Align bar, transportation, photo/video, lighting, guest route, and the couple's departure vehicle. | Coordinator / venue / MC |

# Breakdown and handoffs

| Done | When | Task + confirmation note | Owner |
| --- | --- | --- | --- |
| [ ] | As guests depart | Secure cards, gifts, personal items, and legal documents Use the agreed secure location and document every handoff to the named recipient. | Coordinator / assigned recipient |
| [ ] | During strike | Track vendor pickup, rental counts, leftovers, and trash Photograph unresolved items and use only approved overnight or follow-up pickup plans. | Coordinator / venue / strike leads |
| [ ] | Before leaving | Complete the final venue sweep and key handoff Check every room, vehicle, loading area, storage point, payment handoff, key, and incident note. | Coordinator / venue |

# After the wedding

| Done | When | Task + confirmation note | Owner |
| --- | --- | --- | --- |
| [ ] | Next business day | Send the couple a concise closeout report List completed returns, receipts, damages, lost items, unresolved vendor issues, and required follow-up. | Coordinator |

Turn the confirmed plan into a live timeline: geteventsync.app/free/timeline-builder

# Decision log / follow-up notes

| When | Change, incident, or follow-up | Approved / assigned to |
| --- | --- | --- |