# Wedding Day Timeline Template

A complete 4 PM ceremony example. Replace every sample owner, location, and cue before sharing it.

Recovery key: FIXED = protect the anchor. COMPRESSIBLE = tighten only with approval. BUFFER = protected recovery time. CUTTABLE = optional item to remove first when approved.

# 4 PM ceremony example

| Time | Activity + category | Owner | Location | Notes + recovery cue |
| --- | --- | --- | --- | --- |
| 9:00 AM 9:15 AM | Venue access opens FIXED | Venue contact | Service entrance | Confirm keys or access codes, parking, loading route, and the onsite contact. |
| 9:15 AM 10:30 AM | Rentals and production load-in COMPRESSIBLE | Rentals / production | Service entrance | Photograph delivered inventory and prioritize guest-facing setup first. |
| 10:00 AM 12:00 PM | Floral and decor installation COMPRESSIBLE | Florist / decor | Ceremony and reception spaces | Install ceremony essentials first and identify room-flip pieces. |
| 10:00 AM 1:15 PM | Hair and makeup services COMPRESSIBLE | Hair / makeup | Getting-ready suite | List the service order and a 1:15 PM final-person finish target. |
| 11:00 AM 11:30 AM | Catering and bar load-in FIXED | Catering / bar | Kitchen and bar access | Confirm kitchen access, final counts, dietary notes, and vendor meals. |
| 12:15 PM 12:30 PM | Photographer and videographer arrive FIXED | Photo / video | Getting-ready location | Confirm parking, gear route, coverage end time, and primary contact. |
| 12:30 PM 1:15 PM | Details and room coverage COMPRESSIBLE | Photo / video | Suite and reception room | Gather rings, stationery, attire, flowers, and personal details before coverage begins. |
| 1:15 PM 1:45 PM | Wedding party gets dressed COMPRESSIBLE | Wedding party lead | Getting-ready suite | Keep bouquets, accessories, water, and personal items in one place. |
| 1:45 PM 2:00 PM | Travel buffer to portraits BUFFER | Planner / transportation | Travel route | Verify vehicles, traffic, parking, and the covered backup portrait location. |
| 2:00 PM 2:15 PM | First look COMPRESSIBLE | Photographer | Portrait location | Keep the location private and confirm video is positioned before the couple arrives. |
| 2:15 PM 2:45 PM | Wedding party portraits COMPRESSIBLE | Photographer / wedding party lead | Portrait location | Use a priority shot order so optional combinations can move later if needed. |
| 2:45 PM 3:15 PM | Immediate family portraits COMPRESSIBLE | Photographer / family wrangler | Portrait location | Stage named groups before their turn; the couple should not locate missing relatives. |
| 3:15 PM 3:30 PM | Couple hidden and ceremony reset BUFFER | Planner / venue | Ceremony staging | Move the couple out of guest view and complete the final ceremony readiness check. |
| 3:30 PM 3:55 PM | Guest seating opens FIXED | Ushers / venue | Ceremony space | Confirm reserved seating, programs, water, and the accessible entrance route. |
| 3:50 PM 4:00 PM | Processional lineup and final cue check FIXED | Coordinator / officiant / audio | Ceremony staging | Verify order, rings, license, microphones, music, and the single cue caller. |
| 4:00 PM 4:30 PM | Ceremony FIXED | Officiant / ceremony lead | Ceremony space | Start only after the authorized ceremony lead confirms participants, sound, and guest route are ready. |
| 4:30 PM 5:30 PM | Cocktail hour FIXED | Catering / bar | Cocktail area | Open the guest route, bar, food service, and reception-room work window. |
| 4:35 PM 4:50 PM | Marriage license and private reset COMPRESSIBLE | Couple / officiant / coordinator | Private room | Confirm custody of the license, offer water, and protect a short private pause. |
| 5:10 PM 5:25 PM | Reception room final check FIXED | Venue / catering / DJ | Reception room | Check tables, place settings, lighting, sound, entrances, and an accessible path. |
| 5:30 PM 5:40 PM | Guests seated for dinner COMPRESSIBLE | Venue / ushers | Reception room | Release tables or sections in the agreed order and resolve seating questions away from the couple. |
| 5:40 PM 5:45 PM | Grand entrance FIXED | DJ / MC | Reception room | Line up the wedding party and verify names and pronunciations before announcing. |
| 5:45 PM 5:50 PM | First dance FIXED | DJ / photo / video | Dance floor | Confirm the couple, music track, lighting, and camera teams are ready. |
| 6:00 PM 7:00 PM | Dinner service FIXED | Catering captain | Reception room | Confirm guests are seated, the kitchen is ready, and dietary meals are accounted for. |
| 7:00 PM 7:20 PM | Toasts COMPRESSIBLE | MC / speakers | Reception room | Confirm speaker order, names, microphone, and the catering clearance cue. |
| 7:20 PM 7:35 PM | Parent dances COMPRESSIBLE | DJ / family | Dance floor | Confirm participants, song order, and photo and video readiness. |
| 7:35 PM 7:45 PM | Cake cutting COMPRESSIBLE | Catering / photo / video | Cake table | Bring the couple only after the knife, plates, service plan, and cameras are ready. |
| 7:45 PM 7:55 PM | Optional anniversary dance CUTTABLE | DJ / MC | Dance floor | Remove this first if the timeline is late and the couple or authorized lead approves. |
| 7:55 PM 9:45 PM | Open dancing COMPRESSIBLE | DJ / band | Dance floor | Record band breaks, planned group photos, and any hard bar or transportation cutoff. |
| 9:45 PM 10:00 PM | Last call and transportation reminder FIXED | Bar / MC / transportation | Reception room | State the final bar time and departure options without changing contracted service times. |
| 10:00 PM 10:05 PM | Last song FIXED | DJ / band | Dance floor | Confirm the couple and photo team are present and the exit route is ready. |
| 10:05 PM 10:15 PM | Send-off FIXED | Planner / transportation | Venue exit | Stage guests safely, protect the accessible route, and confirm the couple's vehicle. |
| 10:15 PM 11:15 PM | Strike and final venue sweep FIXED | Venue / planner / vendors | Entire venue | Account for rentals, gifts, cards, personal items, waste, keys, and approved pickup plans. |

# No-first-look variation

Keep the 4 PM ceremony fixed and move the combined portraits into cocktail hour. Confirm the priority groups and family wrangler before the wedding; do not assume every group will fit.

| Time | Activity | Owner | Location | Execution note |
| --- | --- | --- | --- | --- |
| 3:20 PM | Couple remains separate; solo portraits wrap | Photographer / attendants | Getting-ready areas | Protect separate travel and holding routes. |
| 3:30 PM | Guest seating opens | Ushers / venue | Ceremony space | Keep both partners out of guest view. |
| 4:00 PM | Ceremony | Officiant / ceremony lead | Ceremony space | Fixed anchor. |
| 4:35 PM | Immediate family portraits | Photographer / family wrangler | Portrait location | Stage named groups before the recessional ends. |
| 4:55 PM | Wedding party portraits | Photographer / wedding party lead | Portrait location | Use the priority combinations first. |
| 5:15 PM | Couple portraits | Photographer | Portrait location | Hold a private drink and a 5:35 PM hard wrap. |
| 5:30 PM | Guests begin seating for reception | Coordinator / ushers | Reception room | The couple can join at 5:40 PM after a five-minute reset. |
| 5:40 PM | Grand entrance | DJ / MC | Reception room | Keep dinner fire tied to the actual entrance cue. |

# Handoff check

[ ] Confirm every vendor's arrival, setup, service, departure, and best day-of contact.

[ ] Name one authorized person who approves timeline changes and one cue caller for each major transition.

[ ] Keep one approved version and a printed or offline copy. Share role-specific views instead of conflicting master copies.

[ ] Use planned buffers first, then compressible blocks, then cuttable items. SmartRipple suggestions remain advisory; an authorized human approves every change.

Make the sample yours: geteventsync.app/free/timeline-builder

# Decision log / day-of notes

| Time | Change or request | Approved by | People notified |
| --- | --- | --- | --- |